## Instructions
	Instructions

Big picture	A Gap analysis in an implementation project is a highly recommended phase. Its purpose is to present the match of OpenERP with the Customer's needs and convince him on the feasability of the project. It is also the first phase before the first stage gate that allows the Customer to exit the project with limited investment if the results do not conform to his expectations. Even though it is an optional phase, it will make you save time on the detailed analysis. / The goal of a Gap analysis is to determine an estimate of project time and cost at a 70% certainty in a limited time (3 to 15 days).
Steps	1. The Partner interviews the Customer to list the project requirements and their critical level. They might have to define processes to make sure all requirements are covered. / 2. Elico Corp. specifies the functional qualification and the development effort estimation, or asks additional details to Partner and Customer. / 3. Customer reviews the results and can decide to drop certain requirements that would be too expensive or time consuming.
Reuse	This document is a sample, not a template. You can use it: / - to see what the result of a Gap analysis will look like, / - to reuse its structure for your project, / - to understand the level of detail needed to identify the development effort of a requirement. / You should not use the requirements in this document as a starting point to build your own list of requirements because the risk of omitting requirements will increase and their precision related to your project will be altered.
Duration	The time to complete the functional qualification and the development effort estimation is approximately 75 reqs/day once the requirements have a reasonable level of detail. (this sample document presents a reasonable level of detail). / In most cases, the party in charge of identifying the implementation effort will need to ask additional questions on certain requirements that are not clear enough or too specific to the project. Therefore, after the first creation of the requirements list, a discussion will take place with the Partner to make sure they are in line on the meaning of the less meaningful requirements.
Skills	The level of knowledge on OpenERP needed to write the requirements list is small, however it requires to be a business analyst with experience in the field preferably. On the other hand, determining the implementation efforts can only be done by a very exerienced OpenERP analyst because it implies reusing existing functionalities and hence knowing all certified and major modules thoroughly. The official OpenERP Functional Training is certainly a pre-requisite to this.
Approach	To create the list of requirements, the Partner should conduct series of interviews with key people in the organization to identify what information they expect the system will provide them. If listing requirements from scratch is too complex, it is encouraged to first define process diagrams (see technical analysis phase of the project) and list requirements based on each step of these processes to make sure you will not omit any. Moreover, it will save time for the detailed analysis phase.
Working with this document	Each spreadsheet, except the "Results" sheet, represents a need category (Eg: invoicing, production planning, products warranty,...). You can organize them the way you see fit according to your project whether it is by department, by business application, or by project phase. / In each spreadsheet, you will find: / 1. the category name (must be the exact same as the speadsheet name in the tab) / 2. the category subtitle: an optional field to add a description to the name. / 3. the requirements id: a unique identifier per category. / 4. a controller that allows to take or not a requirement into consideration in the results page. / 5. the requirements names: a description that all contributors can relate to similarly. / 6. the critical level: a score between 1 and 4 that represents the importance of the requirement for the contributors from "nice to have" (1) to "MUST have" (4). The contributors team should agree on the meaning of the scale to avoid subjective scoring. Eg: / (4):the company cannot operate without this requirement; / (3):a contributor would waste time on manual processing if this requirement wasn't implemented, this requirement was available in the legacy application; / (2):the OpenERP project is intended to bring new features in addition to the legacy system and this requirement is part of the "why" of this project; / (1):the long-lasting non-critical dream of a contributor. / Moreover, the critical level can be used to determine project phases, starting from the most painful to the least painful for the organization. / 7. the system: the name of the application or system that fulfills the requirements at the moment of the analysis. Eg: MS Excel, Quickbooks, Paper. Use "None" if the requirement is not available and will be introduced with OpenERP. / 8. the contributors: the key people in the organization that are impacted by the requirement and have a decision authority on its implementation. / 9. the OpenERP functional qualification: a description of how Elico Corp. recommends to implement the requirement in OpenERP. / 10. the technical qualification elements: an overview of the technical elements to define during the technical analysis. / 11. the development effort: a score between 1 and 5 that represents the effort it would take OpenERP Inc. to implement the requirement. / (1):Feature already exists as is in OpenERP; / (2):Feature already exists in OpenERP and requires configuration (like a rule or a switch), no development involved; / (3):Feature doesn't exist in OpenERP and requires a small (less than 4 hours) custom development (no change in the existing logic); / (4):Feature doesn't exist in OpenERP and either requires a heavy custom development (more than 4 hours) like a new module or a change in the existing logic; / (5):Not enough information to identify the necessary development (we need more detail)
Contributors	several people holding key roles in the company will contribute to this document (Eg: head accountant, warehouse manager, VP sales,...). The name and subtitle of each sheet has to be meaningful enough so that if a contributor wants to add a requirements, he will know where to find or add it. When a contributor adds a requirement, he must add his name in the contributor list. When a contributor wants to be part of the discussions related to an existing requirement, he must add his name in the contributor list.
Understanding the results	The Gap Frequency Grid shows the frequency of each "critical level-development effort" combination. This grid is the summary of all categories spreadsheets. A red line will appear next to categories that have a score for the critical level and not for the development effort (or vice versa). This is useful to control data integrity. / The development efforts per category is a convenient way of visualizing which categories will require the most effort. / The gap chart shows the distribution "critical level-effort". It helps determining the part of the project that will be the most crucial (score 4-4). It also allows to potentially remove from the project scope the requirements with a high effort and a low critical level to decrease the total budget. / The total time and cost estimation: / takes the OpenERP qualification into account to determine the time and hence cost necessary for the analysis phase, and / takes the development effort into account to determine the time and hence cost necessary for the development phase.

## Consolidation
For headers
					Functional Analysis					Technical Analysis					Development		Test	Estimated Investment
					Reports		Processes		Screens		Workflows					Wizards
#	Control	Category	Functionality	Description	Critical Level	Phase	Contributors	OpenERP Solution Mapping	range1	range2	range3	range4	range5	range6	range7	range8	range9	range10	range11	range12	range13	range14	range15	Effort	# hours if Effort=4		currency	Analysis	Dev
/For headers
For lines
cpt	keep	fct_category	functionality	description	critical	phase	contributor	openerp_fct	cost1	cost2	cost3	cost4	cost5	cost6	cost7	cost8	cost9	cost10	cost11	cost12	cost13	cost14	cost15	effort	effort2day	testing	total_cost	total_analysis	total_dev
/For lines

## Results
Gap Chart
Implementation Effort
Critical Level